## Sheet1
Phase | Project # | Project | FY20/21 |  |  | FY21/22 |  |  | FY22/23 |  |  | FY23/24 |  |  | FY24/25
|  |  | Jul. - Sep. | Oct. - Mar. | Apr. - Jun. | Jul. - Sep. | Oct. - Mar. | Apr. - Jun. | Jul. - Sep. | Oct. - Mar. | Apr. - Jun. | Jul. - Sep. | Oct. - Mar. | Apr. - Jun. | Jul. - Sep. | Oct. - Mar. | Apr. - Jun.
0 |  | Pre-construction activities | Approval of Transportation System Plan updates (August)
0 |  | Pre-construction activities |  |  | Final engineering for Phase 1 project elements
0 |  | Pre-construction activities |  |  | ROW acquisition based on final engineering plans (June)
0 |  | Pre-construction activities |  |  | Contracting- Bid prep and RFP's, Review and Award (May and June)
1 | 1 | 7th Street West Extension |  |  |  | Rough-in road, pipe, base rock, grading |  | Curb, sidewalks, paving
1 | 2 | Government Entry Road | [6 empty] | Rough-in road, pipe, base rock, grading |  | Paving
1 | 3 | Gateway Drive | [6 empty] | Rough-in road, pipe, base rock, grading |  | Curb, sidewalks, paving
1 | 4 | Ironwood Estates |  |  |  | Rough-in road, pipe, base rock, grading
1 | 5 | Highway 26 & I.G. Improvements |  |  |  | Rough-in road, pipe, base rock, grading |  | Final grading, compaction
1 | 6 | Johnson DR Drive |  |  |  | Rough-in road, pipe, base rock, grading |  | Paving
1 | 7 | Charolais Heights Intersection |  |  |  | Rough-in road, pipe, base rock, grading |  | Final grading, compaction
1 | 8 | Integrated Parks System Transportation Infrastructure |  |  |  | Bridge foundation and trail and parking lot grading | Decking and railing | Paving
2 | 9 | 7th Street East Extension & Holmstrom Bridge and Road | [6 empty] | Final engineering | ROW acquisition based on final engineering plans | Contracting- Bid prep and RFP's, Review and Award | Bridge Foundation/Deck Rough-in road, pipe, base rock, grading |  | Curb, sidewalks, paving
2 | 10 | Downtown Parking Improvements | [6 empty] | Final engineering |  | Contracting- Bid prep and RFP's, Review and Award |  |  | Curb, sidewalks, paving
2 | 11 | Mahogany Ridge Housing | [6 empty] | Final engineering | ROW acquisition based on final engineering plans | Contracting- Bid prep and RFP's, Review and Award | Rough-in road, pipe, base rock, grading |  | Paving